## Sheet1
Feature | Initial Estimate | Week 1 | Week 2 | Week 3 | Week 4
GitHub Repository | 11 | 2 | 5 | 1 | 1
GitHub Project | 11 | 2 | 1 | 2 | 3
Documentation | 11 | 4 | 5 | 1 | 2
Settting | Start | Week 1 | Week 2 | Week 3 | Week 4
Planned Hours |  | 8.25 | 8.25 | 8.25 | 8.25
Actual Hours |  | 8 | 11 | 4 | 6
Remaining Effort | 33 | 25 | 14 | 10 | 4
Ideal Burndown | 33 | 24.75 | 16.5 | 8.25 | 0